SILLA — Space Intelligence & Live Layout Administration

Scrum Workflow — Product Backlog & Sprint Plan  ·  v2  ·  Six-Week Timeline

# Scrum Framework

The project runs as three two-week sprints across a six-week timeline, a tightened revision of the original eight-week plan to fit a commercial, multi-vertical rebuild of the system. Work is pulled from the backlog into each sprint according to the sprint goal and the team's capacity.

## Roles

•	Product Owner  — owns the backlog and priorities.

•	Scrum Master / Project Manager  — facilitates the process, removes blockers, protects sprint scope.

•	Development Team  — designs, builds, and tests each increment.

## Ceremonies

•	Sprint Planning, Daily Scrum, Sprint Review, Sprint Retrospective  — standard cadence at the start, throughout, and end of each two-week sprint.

## Conventions

•	Estimation  — Fibonacci story points (1, 2, 3, 5, 8).

•	Prioritization  — MoSCoW: Must, Should, Could.

Definition of Done  — merged to main, code-reviewed, tested, demo-able on staging.

# What Changed From v1

•	Scope, not NU-specific: the system is rebuilt as a white-label, multi-vertical platform (SILLA), not an NU Laguna–only tool. All NU-specific content is removed.

•	Timeline compressed: eight weeks / four sprints → six weeks / three sprints.

•	New foundation work added: the org / site / floor hierarchy, the configuration schema, and the check-in abstraction (E0) did not exist in v1 and are now Sprint 1 priorities.

•	Some v1 scope deferred: the audit-log tab, presence / find-a-member lookup, scheduled export, and advanced analytics move from “in scope” to the explicit roadmap, to make the six-week timeline realistic.

# Epics

•	E0 — Foundation, Config & Deployment  (5 stories, 23 pts)

•	E1 — Identity & Registration  (3 stories, 11 pts)

•	E2 — Authentication & Access  (4 stories, 12 pts)

•	E3 — Resource Catalog & Space Map  (6 stories, 33 pts)

•	E4 — Reservations  (7 stories, 29 pts)

•	E5 — Occupancy & Check-In  (6 stories, 23 pts)

•	E6 — Notifications  (5 stories, 15 pts)

•	E7 — Admin Surface & Settings  (5 stories, 28 pts)

•	E8 — Analytics & Reporting  (1 stories, 5 pts)

# Product Backlog

## E0  ·  Foundation, Config & Deployment

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| INF-1 | As a developer, I want the org / site / floor data model scaffolded so every deployment has one consistent hierarchy. AC: Org, site, floor, and grid documents modeled and related; One deployment maps to one organization. | 5 | Must |
| INF-2 | As a developer, I want a per-organization configuration record so branding, terminology, and policy values are never hardcoded. AC: One config document per org covers identity, terminology, check-in, policy numbers, privacy, content; Read at runtime by the relevant features. | 5 | Must |
| INF-3 | As a developer, I want the check-in step built behind one interface so a second method can be added later without a rewrite. AC: resolveCheckIn(credential) abstraction in place; RFID is the only implementation in v1. | 5 | Must |
| INF-4 | As a developer, I want an RFID read spike so we confirm a card UID reaches the database through the check-in interface. AC: A tapped UID is captured and stored via the interface; Timeboxed; go / no-go recorded. | 3 | Must |
| INF-5 | As a developer, I want the app deployed to AWS with the worker running so it is demoable on staging. AC: Deployed; worker runs; Meets 'demo-able on staging' DoD. | 5 | Must |

## E1  ·  Identity & Registration

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| ID-1 | As a member, I want to self-register in person at a kiosk by tapping my card so my account is bound to my ID. AC: Tap captures UID; unregistered → registration; Captures configurable-format member ID, email, name, 6-digit PIN. | 5 | Must |
| ID-2 | As a member, I want to verify my email with a code during registration so my account is confirmed reachable. AC: Code emailed and entered at kiosk; Account stays pending until verified. | 3 | Must |
| ID-3 | As the system, I want member ID, email, and card UID unique and 1:1 within an organization so no duplicates exist. AC: DB-level unique constraints scoped to the org; Duplicate attempts rejected clearly. | 3 | Must |

## E2  ·  Authentication & Access

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| AUTH-1 | As a user, I want to log in with my email and 6-digit PIN so I can access the system regardless of role. AC: Validates email + PIN; Same login for members and staff. | 3 | Must |
| AUTH-2 | As the system, I want to rate-limit and lock out repeated wrong PINs so accounts resist brute force. AC: Lockout after N wrong attempts; Applies on web and kiosk. | 3 | Must |
| AUTH-3 | As a first-time user, I want to accept terms before using the app so responsibilities are acknowledged. AC: First-login flag routes to terms; Cannot proceed until accepted. | 3 | Must |
| AUTH-4 | As a member, I want to reset my PIN so I can recover access. AC: Reset flow via email; New PIN set and usable. | 3 | Should |

## E3  ·  Resource Catalog & Space Map

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| CAT-1 | As SILLA (vendor), I want to configure a resource catalog per organization at install so each deployment reflects its own bookable resources. AC: Catalog seeded per org from a fixed piece-type model; Different orgs can have different catalogs. | 5 | Must |
| MAP-1 | As a member, I want to see a live, multi-floor map so I can view resource availability at a glance. AC: Read-only SVG grid; floor switcher; status shown by colour + icon; Responsive with pan / zoom on mobile. | 8 | Must |
| MAP-2 | As the system, I want resource status changes to update the map in real time so everyone sees current availability. AC: Socket.io pushes status changes; Layout and live status kept separate. | 5 | Must |
| MAP-3 | As an admin, I want to place and remove catalog resources on a grid so the map reflects the real floor. AC: Pick from catalog; click cell to place / remove; Overlap prevented by occupied-cell check. | 8 | Must |
| MAP-4 | As an admin, I want to draw named zones so resources are grouped for management and analytics. AC: Drag rectangle; name it; Membership derived from position. | 5 | Should |
| MAP-5 | As an admin, I want free-typed labels so members can orient themselves on the map. AC: Place text anywhere; non-reservable; Excluded from analytics. | 2 | Could |

## E4  ·  Reservations

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| RES-1 | As a member, I want to reserve a resource by selecting it and confirming with my PIN so I secure it. AC: Select available resource + time; card + PIN confirm; Resource held on confirm. | 5 | Must |
| RES-2 | As the system, I want resource claims atomic and time-range based so no double-booking occurs. AC: Server-side atomic claim; Overlapping-time reservations rejected. | 8 | Must |
| RES-3 | As the system, I want self-only, one-active reservations so resources aren't hoarded. AC: One active reservation per member; Reserving on behalf of others not possible. | 3 | Must |
| RES-4 | As a member, I want to reserve near others using a group code so we can be placed together. AC: First reserver gets a code; others enter it; Nearby open resources highlighted. | 5 | Should |
| RES-5 | As a member, I want a grace period to check in so I have time to arrive. AC: Configurable default; resource held during grace; Expiry releases resource and marks no-show. | 3 | Must |
| RES-6 | As staff, I want to adjust the grace period so busy periods can be tightened. AC: Adjustable in Settings; Notice posted and that day's reservers emailed. | 2 | Should |
| RES-7 | As the system, I want the reservation engine to respect organization status and closures so no one books a closed period. AC: Validation checks status / closures; Blocked periods unselectable. | 3 | Must |

## E5  ·  Occupancy & Check-In

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| OCC-1 | As a member, I want to check in by tapping so my reservation activates. AC: Tap resolves via the check-in interface; within grace → occupied; Handled per resource. | 5 | Must |
| OCC-2 | As a walk-in, I want to tap and pick an open resource so I can use it without a reservation. AC: No reservation → map shown; Selected open resource assigned on the spot. | 5 | Must |
| OCC-3 | As a member, I want to check out by tapping so my resource frees for others. AC: Tap out frees the resource; Map updates immediately. | 3 | Must |
| OCC-4 | As the system, I want resources auto-released after the configured maximum stay so they don't stay locked. AC: Worker releases at the org's configured cap; Member emailed; session flagged overstay. | 5 | Must |
| OCC-5 | As the system, I want forgotten checkouts released at closing so occupancy resets daily. AC: Released using the org's configured operating hours. | 3 | Must |
| OCC-6 | As the system, I want duplicate taps within 5s ignored so accidental double-taps don't error. AC: Second identical tap within 5s ignored; Kiosk shows a brief timer. | 2 | Should |

## E6  ·  Notifications

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| NOT-1 | As a developer, I want an async email layer via an email API so mail never blocks or breaks a reservation. AC: Emails sent async; A mail failure never rolls back a reservation. | 5 | Must |
| NOT-2 | As a member, I want a confirmation email when I reserve so I have a record. AC: Email sent on reservation confirm. | 2 | Must |
| NOT-3 | As a member, I want a starting-soon reminder so I don't miss my grace window. AC: Worker sends reminder before grace; Sent-once flag prevents duplicates. | 3 | Must |
| NOT-4 | As a member, I want an email when my session is auto-released so I know my resource was freed. AC: Email sent on max-stay release. | 2 | Should |
| NOT-5 | As a member, I want an email if a closure cancels my reservation so I'm informed with a reason. AC: Closure cancels reservations and emails; Staff-entered reason included. | 3 | Must |

## E7  ·  Admin Surface & Settings

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| ADM-1 | As staff, I want a live dashboard so I can monitor the space at a glance. AC: Metrics: occupied, open / total, overstays; live map per floor; Overstay flagged for staff; metric click highlights resource. | 5 | Must |
| ADM-2 | As staff, I want a Resources & Rules view so I can manage availability and view schedules. AC: Grace / cap controls; grouped-by-zone list; per-resource schedule + history; Toggle availability; cancel a reservation. | 5 | Must |
| ADM-3 | As staff, I want a Members & Cards view so I can look up members and reissue cards. AC: Search; table with current session; history + PIN reset; Reissue: tap new card, duplicate check, confirm, invalidate old. | 5 | Must |
| ADM-4 | As a superadmin, I want to create and manage staff so I control who has access. AC: Create staff (role, name, email → OTP); forced first-login PIN change; Reset, change role, deactivate; superadmin locked. | 5 | Must |
| ADM-5 | As a superadmin, I want a Settings view so I control status, hours, closures, and the white-label configuration. AC: Status enforced on reservations; scheduled closure with reason, cancellation, and emails; Operating hours, notices, manual filtered export, branding & terminology config. | 8 | Must |

## E8  ·  Analytics & Reporting

| ID | User Story & Acceptance Criteria | Pts | Pri |
| --- | --- | --- | --- |
| RPT-1 | As an administrator, I want basic usage reports so I can plan the space. AC: Peak hours, average occupancy, no-show / overstay rate; Advanced trends and heatmaps are fast-follow. | 5 | Should |

# Sprint Plan

## Sprint 0 · Foundation, Identity & Map

Sprint goal: The foundation is real: an organization can be configured, a member can register and log in via RFID, and the live multi-floor map renders.

| ID | Backlog Item | Pts |
| --- | --- | --- |
| INF-1 | Org / site / floor data model | 5 |
| INF-2 | Configuration schema (white-label) | 5 |
| INF-3 | Check-in interface (RFID now, QR-ready) | 5 |
| INF-4 | RFID read spike (timeboxed) | 3 |
| ID-1 | Kiosk self-service registration | 5 |
| ID-2 | Email verification code | 3 |
| ID-3 | Uniqueness (1:1 identity) | 3 |
| AUTH-1 | Login (email + PIN) | 3 |
| AUTH-2 | Rate-limit + lockout | 3 |
| AUTH-3 | First-login terms acceptance | 3 |
| CAT-1 | Vendor-configured catalog per install | 5 |
| MAP-1 | Live space map (read-only, multi-floor) | 8 |
| Sprint total |  | 51 |

## Sprint 2 · Reservation Engine & Physical Loop

Sprint goal: The core loop works end to end: a member can reserve a resource, have it genuinely held, check in and out, and receive email confirmation.

| ID | Backlog Item | Pts |
| --- | --- | --- |
| AUTH-4 | PIN reset | 3 |
| MAP-2 | Real-time map updates | 5 |
| MAP-3 | Resource placement (editor) | 8 |
| RES-1 | Reserve a resource | 5 |
| RES-2 | Atomic time-range claim | 8 |
| RES-3 | Self-only, one active | 3 |
| RES-4 | Group code | 5 |
| RES-5 | Grace period + expiry | 3 |
| RES-7 | Status / closure check | 3 |
| OCC-1 | Check-in by tap | 5 |
| OCC-2 | Walk-in resource selection | 5 |
| OCC-3 | Check-out by tap | 3 |
| OCC-4 | Max-stay cap + overstay flag | 5 |
| OCC-5 | Closing-time auto-release | 3 |
| OCC-6 | Duplicate-tap idempotency | 2 |
| NOT-1 | Async email layer | 5 |
| NOT-2 | Reservation confirmation email | 2 |
| NOT-3 | Starting-soon reminder | 3 |
| Sprint total |  | 76 |

## Sprint 3 · Admin Surface, Hardening & Delivery

Sprint goal: The system is administrable, deployed, and ready to demo or pitch as a commercial product.

| ID | Backlog Item | Pts |
| --- | --- | --- |
| INF-5 | Deploy to AWS + harden staging | 5 |
| MAP-4 | Zone drawing | 5 |
| MAP-5 | Free-typed labels | 2 |
| RES-6 | Staff-adjustable grace | 2 |
| NOT-4 | Overstay-release email | 2 |
| NOT-5 | Closure-cancellation email | 3 |
| ADM-1 | Dashboard (metrics + live map) | 5 |
| ADM-2 | Resources & Rules | 5 |
| ADM-3 | Members & Cards + reissue | 5 |
| ADM-4 | Staff management + onboarding | 5 |
| ADM-5 | Settings (status / closures / config) | 8 |
| RPT-1 | Basic usage reports | 5 |
| Sprint total |  | 52 |

Capacity note: Sprint 3 carries the heaviest admin scope. If behind, zones/labels (MAP-4, MAP-5) and basic reports (RPT-1) are the first candidates to push into the fast-follow roadmap.

Total committed: 179 story points across 6 weeks. Recalibrate against actual velocity after Sprint 1.

# Fast-Follow Roadmap (Not in These Sprints)

•	QR check-in  — second implementation behind the existing check-in interface.

•	Configurable check-in & onboarding mode  — buyer chooses RFID / QR / both, and self-service vs. provisioned registration.

•	Presence / find-a-member lookup  — with configurable visibility (off / opt-in / team-scoped).

•	Audit logs, richer analytics, scheduled export  — deferred from v1 to keep the six-week timeline realistic.

•	Multi-site management UI  — data model supports it now; UI does not exist yet.

•	Buyer-facing catalog editor  — letting an organization define its own resource types.

•	True multi-tenant platform  — one deployment serving many organizations with isolated data; deliberately out of scope.